## Slide 1
Logical Framework Matrix - Theory of Changes
Gantt Chart - Pert Diagram (WPs and Tasks)- Useful Tables/Charts
Business Model Canvas – Business Plan
SESSION 6: Plan Effectively for a Competitive Research Proposal
The PRIMA programme is an Art.185 initiative supported and funded under Horizon 2020, the European Union’s Framework Programme for Research and Innovation.
For demonstration purpose only. Not part of the PRIMA official template

## Slide 2
trategic Research and Innovation Agenda
raft - August 10th 2017
1. Logical Framework Matrix - Theory of Changes
This training material has been prepared via PRIMA-IS for training purpose only.
For demonstration purpose only. Not part of the PRIMA official template

## Slide 3
Current negative situation
Core problem
Causes
Effects
But why?
So what?
Problem Analysis
This training material has been prepared via PRIMA-IS for training purpose only.
Problem Tree
Cause-effect analysis
For demonstration purpose only. Not part of the PRIMA official template

## Slide 4
Current negative situation
Positive desirable situation
Core problem
Causes
Effects
Key Objective
Possible outputs and activities
Possible impact and indicators
Problem Analysis
This training material has been prepared via PRIMA-IS for training purpose only.
For demonstration purpose only. Not part of the PRIMA official template
MY PROJECT

## Slide 5
trategic Research and Innovation Agenda
raft - August 10th 2017
Result chain |  | Indicators | Baseline | Target | Means of Verification | Assumptions
Impact |  |  |  |  |  | 
Outcomes |  |  |  |  |  | 
Output 1 |  |  |  |  |  | 
Activities 1.1… |  |  |  |  |  | 
Output 2 |  |  |  |  |  | 
Activities 2.1… |  |  |  |  |  | 
Logical Framework Matrix
This training material has been prepared via PRIMA-IS for training purpose only.
For demonstration purpose only. Not part of the PRIMA official template
Stage 2, Full Application (Excellence OR Impact)

## Slide 6
trategic Research and Innovation Agenda
raft - August 10th 2017
Result chain |  |  | Indicators | Baseline | Target | Means of Verification | Assumptions
Impact/ General Objective/ Purpose |  | The long-term development improvement/positive change to which a project/program is intended to contribute. |  |  |  |  | 
Outcome / Specific Objective OC1 or SO1 |  | A change in behavior, to which research outputs and related activities have contributed. |  |  |  |  | Necessary conditions for the outcome to lead to the impact
Output or Deliverables OP1 or D1 |  | Knowledge, technical or institutional advancement produced by the project’s research, engagement and/or capacity development activities. |  |  |  |  | Necessary conditions for the output(s) to lead to the achievement of the outcome
Activities A1.1… |  |  |  |  |  |  | Necessary conditions for the activities to lead to the achievement of the related output
Output OP2 |  |  |  |  |  |  | 
Activities 2.1… |  |  |  |  |  |  | 
Logical Framework Matrix
This training material has been prepared via PRIMA-IS for training purpose only.
For demonstration purpose only. Not part of the PRIMA official template

## Slide 7
trategic Research and Innovation Agenda
raft - August 10th 2017
Result chain |  | Indicators | Baseline | Target | Means of Verification | Assumptions
Impact |  | Quantitative or qualitative metrics that can verify changes relative to what was planned | The situation relative to the indicator prior to project implementation against which progress can be assessed | Level of performance relative to the indicator that the project is projected to accomplish in a given time period | The data sources or reporting mechanisms that specify how the indicator data will be collected | 
Outcome |  |  |  |  |  | 
Output 1 |  |  |  |  |  | 
Activities 1.1… |  |  |  |  |  | 
Output 2 |  |  |  |  |  | 
Activities 2.1… |  |  |  |  |  | 
Logical Framework Matrix
This training material has been prepared via PRIMA-IS for training purpose only.
7
For demonstration purpose only. Not part of the PRIMA official template

## Slide 8
Sphere of control
Sphere of interest
Sphere of Influence
Problem analysis / rationale
Inputs $
Work package
Output 2
Outcome(s)
Impact
SDGs
National Priorities
PRIMA Topic/ SRIA
Risks
Assumptions
How?
What?
Why?
The greater why?
Output 1
Output 3
Work package
Work package
Assumptions
Assumptions
Assumptions
The Theory of Change of Your Project
This training material has been prepared via PRIMA-IS for training purpose only.
For demonstration purpose only. Not part of the PRIMA official template
Stage 2, Full Application (Impact)

## Slide 9
trategic Research and Innovation Agenda
raft - August 10th 2017
2. Gantt Chart – PERT Diagram
This training material has been prepared via PRIMA-IS for training purpose only.
9
For demonstration purpose only. Not part of the PRIMA official template

## Slide 10
Gantt Chart – example
2020
2021
2022
06
07
08
09
Work Package Name
WP1: Co-ordination and Project Management
WP2: Dissemination and Exploitation
WP3: Assessment and Evaluation
WP1.1:
WP1.2:
WP2.1:
WP2.2:
WP2.3:
WP3:
Milestones
Deliverables
D01
M1
M2
D121
D122
D123
M3
M4
M5
D211
D221
D231
D241
M6
D311
D321
D331
M7
D411
D421
D431
D441
WP2.4:
WP4:
10
11
12
06
07
08
09
10
11
12
01
02
03
04
05
01
02
03
04
05
This training material has been prepared via PRIMA-IS for training purpose only.
10
For demonstration purpose only. Not part of the PRIMA official template
Stage 1- Pre Proposal (Excellence)
Stage 2 – Full Proposal (Implementation)

## Slide 11
This training material has been prepared via PRIMA-IS for training purpose only.
11
For demonstration purpose only. Not part of the PRIMA official template
Stage 1- Pre Proposal (Excellence)
Stage 2 – Full Proposal (Implementation)
Work Packages - Task Allocation (PERT Diagram)

## Slide 12
Work Packages - Task Allocation (PERT Diagram)
This training material has been prepared via PRIMA-IS for training purpose only.
12
For demonstration purpose only. Not part of the PRIMA official template

## Slide 13
WPs/ Leader | TASKS | Timeline | Resp. Partner/ Involved Partners | Main Deliverables
WP1: XX1 (WPL: P1) | Task 1.1 - | M1-M8 |  | D1.1, D1.2
 | T1.2 - | M1-M7 |  | 
 | T1.3 – | M8-M26 |  | 
WP2: XX2 (WPL: P4) | T2.1 - | M4-M5 |  | D2.1, D2.2, D2.3
 | T2.2 - | M4-M9 |  | 
 | T2.3 - | M4-M9 |  | 
WP3: XX3 (WPL: P2) | T3.1 - | M10-M11 |  | D3.1, D3.2, D3.3
 | T3.2 - | M12-M18 |  | 
Work Packages - Task Allocation (Table)
This training material has been prepared via PRIMA-IS for training purpose only.
13
For demonstration purpose only. Not part of the PRIMA official template
Stage 1- Pre Proposal (Excellence)
Stage 2 – Full Proposal (Implementation)

## Slide 14
Some Useful Tables
This training material has been prepared via PRIMA-IS for training purpose only.
14
For demonstration purpose only. Not part of the PRIMA official template
Stage 1- Pre Proposal (Excellence)
Stage 2 – Full Proposal (Implementation)
PRIMA Topic Challenges & Scope | Project Response
Call Challenge | 
PRIMA SRIA Objective | 
Topic Scope | 
WP Title | Start Date | End Date | Resp. Partner | Deliverables
WP1… | M1 | M5 | P1 | D1.1….
WP2… | M3 | M10 | P2 | D2.2….
WPn…. | M23 | M36 | P1 | Dn.1…..
Technology | Initial TRL | Developed Solution | Final TRL
Technology 1 | 3 | New Tech.1 | 6
Technology 2 | 3 | New Tech.2 | 7
Technology 3 | 4 | New Tech.3 | 6
Communication Action | KPIs | Target Audiences
Website | 1 | Public
Leaflets | 1000 | Scientific communities in…
Workshops | 4 | Smallholders in….
TG/FB | Demands & Challenges | Project Response
[Target Group 1] |  | 
[Final Beneficiary 1] |  | 
[Target Group 3] |  | 

## Slide 15
Some Useful Charts
This training material has been prepared via PRIMA-IS for training purpose only.
For demonstration purpose only. Not part of the PRIMA official template
Chart: Gender Balance
| Male | Female
Sales | 45 | 55
Chart: 
| EU Budget | MPC Budget
Budget Shares | 60 | 40
Chart: WP Budget Shares
| WP1 | WP2 | WP3 | WP4 | WP5
Budget Shares | 10 | 10 | 25 | 40 | 10

## Slide 16
trategic Research and Innovation Agenda
raft - August 10th 2017
3. Business Model Canvas – Business Plan
This training material has been prepared via PRIMA-IS for training purpose only.
16
For demonstration purpose only. Not part of the PRIMA official template

## Slide 17: Business Model Canvas
1
2
3
4
5
6
7
9
8
Stage 1/2 – Full Proposal (Excellence OR Impact)
This training material has been prepared via PRIMA-IS for training purpose only.

## Slide 18: Business Plan – in BRIEF
Source: https://smartasset.com/small-business/top-components-of-a-business-plan
Summary.
Product Description.
Market Analysis.
Competitive Analysis/ available Alternatives and USPs.
Tentative Marketing and Sales Plan.
Budgeting and Use of Resources
Financial Projection of the Final Products
Management and Organization
For demonstration purpose only. Not part of the PRIMA official template
Stage 1/2 – Full Proposal (Excellence OR Impact)
This training material has been prepared via PRIMA-IS for training purpose only.

## Slide 19
@PRIMAProgram
Prima Program
Prima-med YouTube
PrimaProgram
Dr. Mohamed Wageih
Project Officer
PRIMA – The Partnership for Research and Innovation in the Mediterranean Area
mohamed.wageih@prima_med.org
END OF SESSION FIVE THANK YOU FOR YOUR ATTENTION